## TestPlan
PlantChoice (GreenMean) Project |  |  |  |  | Test Plan
Test Plan Identifier: | PlantChoice Test Plan
Introduction: | To define testing strategy for the project
Objectives: | Ensure that all functionalities meet specified requirements
Test Scope: | This test covers all functionalities required
Date: | 2025-08-12 |  |  | Updated on: 12/10/25
Test Case | Test Item | Test Environment & Tools | Test Types | Test Strategy and Approach |  | Entry Criteria | Exit Criteria | Start Date | End Date | Status | Assignee | Notes
TC-01 | Navigation Bar | Desktop Browser (Microsoft Edge) | functional | functional test |  | Navigation bar is availabe in dashboard page | All test cases are passed successfully after completion or fixing | 2025-08-11 | 2025-08-17 | Passed | Yongzhen Jiang
TC-02 | PythonAnywhere Deployment | Desktop Browser (Microsoft Edge) | functional | functional test |  | Application is deployed to PythonAnywhere | All test cases are passed successfully after completion or fixing | 2025-08-11 | 2025-08-17 | Passed | Yongzhen Jiang
TC-03 | Survey Process (Desktop) | Desktop Browser (Microsoft Edge) | functional | functional test |  | Survey process is done | All test cases are passed successfully after completion or fixing | 2025-08-11 | 2025-08-17 | Passed | Yongzhen Jiang
TC-04 | Survey Process (Mobile) | iPhone 14 | functional | functional test |  | Survey process is done | All test cases are passed successfully after completion or fixing | 2025-08-11 | 2025-08-17 | Passed | Yongzhen Jiang
TC-05 | Survey UI styles | Desktop Browser (Microsoft Edge) | functional | functional test |  | Survey pages have been updated with UI via tailwind CSS | All test cases are passed successfully after completion or fixing | 2025-08-18 | 2025-08-24 | Passed | Yongzhen Jiang
TC-06 | plant name display after survey completion | Desktop Browser (Microsoft Edge) | functional | functional test |  | Survey completion page has been updated | All test cases are passed successfully after completion or fixing | 2025-08-18 | 2025-08-24 | Passed | Yongzhen Jiang
TC-07 | ranking of Bradley-Terry model scores | Desktop Browser (Microsoft Edge) | functional | functional test |  | Bradley-Terry model calculation including ranking of scores are done | All test cases are passed successfully after completion or fixing | 2025-08-18 | 2025-08-24 | Passed | Yongzhen Jiang
TC-08 | Bradley-Terry mode calculation based on database source rather than static mock data | Desktop Browser (Microsoft Edge) | functional | functional test |  | Bradley-Terry model calculation has been switched to be based on database data | All test cases are passed successfully after completion or fixing | 2025-08-18 | 2025-08-24 | Passed | Yongzhen Jiang
TC-09 | response time recording | Desktop Browser (Microsoft Edge) | functional | functional test |  | Response time for each choice is saved to database | All test cases are passed successfully after completion or fixing | 08/09/2025 | 2025-09-14 | Passed | Yongzhen Jiang
TC-10 | weighted Bradley-Terry model | Desktop Browser (Microsoft Edge) | functional | functional test |  | Weighted version of Bradley-Terry model calculation is completed | All test cases are passed successfully after completion or fixing | 08/09/2025 | 2025-09-14 | Passed | Yongzhen Jiang
TC-11 | raw data display and downloading | Desktop Browser (Microsoft Edge) | functional | functional test |  | Raw data display and download function are completed | All test cases are passed successfully after completion or fixing | 08/09/2025 | 2025-09-14 | Passed | Yongzhen Jiang
TC-12 | survey cycle function | Desktop Browser (Microsoft Edge) | functional | functional test |  | Survey cycle function has been implemented | All test cases are passed successfully after completion or fixing | 08/09/2025 | 2025-09-14 | Passed | Yongzhen Jiang
TC-13 | end user testing | Mobile Phone (iPhone & Andriod Phone) | functional | functional test |  | The whole website is ready for end user testing | All test cases are passed successfully after completion or fixing | 2025-09-15 | 2025-09-21 | Passed | end users (some students)
TC-14 | survey cycle data downloading function | Desktop Browser (Microsoft Edge) | functional | functional test |  | Survey cycle data download function is ready | All test cases are passed successfully after completion or fixing | 2025-09-15 | 2025-09-21 | Passed | Yongzhen Jiang
TC-15 | inversed response time as weighting | Desktop Browser (Microsoft Edge) | functional | functional test |  | Development of inversed response time as weighting is completed | All test cases are passed successfully after completion or fixing | 2025-09-15 | 2025-09-21 | Passed | Yongzhen Jiang
TC-16 | quick naviation button in dashboard page | Desktop Browser (Microsoft Edge) | functional | functional test |  | The quick navigation function has been deployed | All test cases are passed successfully after completion or fixing | 2025-09-15 | 2025-09-21 | Passed | Yongzhen Jiang
TC-17 | API function calling OpenAI nano model | HttpPie | api | api test |  | OpenAI api calling function is successful | All test cases are passed successfully after completion or fixing | 2025-09-22 | 2025-09-28 | Passed | Yongzhen Jiang
TC-18 | AI generated plant introduction | Desktop Browser (Microsoft Edge) | functional | functional test |  | Function of AI generated plant introduction has been completed | All test cases are passed successfully after completion or fixing | 2025-09-22 | 2025-09-28 | Passed | Yongzhen Jiang
TC-19 | typing effect of the AI generated description of the plant | Desktop Browser (Microsoft Edge) | functional | functional test |  | Typing effect of the plant description text is ready for test | All test cases are passed successfully after completion or fixing | 2025-09-22 | 2025-09-28 | Passed | Yongzhen Jiang
TC-20 | plant list and plant adding and editing | Desktop Browser (Microsoft Edge) | functional | functional test |  | The UI styles of plant list and plat adding/editing has been completed | All test cases are passed successfully after completion or fixing | 2025-09-22 | 2025-09-28 | Passed | Yongzhen Jiang
TC-21 | profile edit | Desktop Browser (Microsoft Edge) | functional | functional test |  | Styles of profile edit page has been updated | All test cases are passed successfully after completion or fixing | 2025-09-29 | 05/10/2025 | Passed | Yongzhen Jiang
TC-22 | survey cycle master detail tables | Desktop Browser (Microsoft Edge) | functional | functional test |  | Master-detail tables for survey cycle have been developed | All test cases are passed successfully after completion or fixing | 2025-09-29 | 05/10/2025 | Passed | Yongzhen Jiang
TC-23 | survey cycle summary table | Desktop Browser (Microsoft Edge) | functional | functional test |  | Survey summary table function has been completed and is ready for testing | All test cases are passed successfully after completion or fixing | 2025-09-29 | 05/10/2025 | Passed | Yongzhen Jiang

## TestCase-01
Testing Case for Navigation Bar
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-01 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
12/08/2025 | 1 | Logging in | Should be able to login in successfully | Logged in successfully | PASS | Yongzhen Jiang | No issues
12/08/2025 | 2 | Click the dashboard menu | 1. The overall tab page is displayed 2. The percentage and count displays correctly 3. The bar chart displays correctly | The overall page displays and the percentage, count and bar charts display correct. | PASS | Yongzhen Jiang | No issues
12/08/2025 | 3 | Click the By Age Group Tab | 1. The By Age Group tab page is displayed 2. The percentage and count displays correctly for each age group 3. The bar chart displays correctly | The by age group tab page displays and the percentage, count and bar charts display correct. | PASS | Yongzhen Jiang | No issues
12/08/2025 | 4 | Click the By Gardening Tab | 1. The By Gardening tab page is displayed 2. The percentage and count displays correctly for each group 3. The bar chart displays correctly | The by gardening tab page displays and the percentage, count and bar charts display correct. | PASS | Yongzhen Jiang | No issues
12/08/2025 | 5 | Click the Bradley-Terry Model Tab | 1. The bradley-terry model tab page is displayed 2. Statiscal charts can be displayed | Charts show successfully | PASS | Yongzhen Jiang | No issues

## TestCase-02
Testing Case for PythonAnywhere Deployment
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-02 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
12/08/2025 | 1 | Visit PythonAnywhere URL | The website works and is accessible | The URL is publicly available | PASS | Yongzhen Jiang | No issues
12/08/2025 | 2 | Click Start Survey | The survey can be conducted without issue | Survey was conducted and completed | PASS | Yongzhen Jiang | No issues
12/08/2025 | 3 | Login as admin user | Admin user can log in and view dashboard page | Can login and view internal dashboard pages | PASS | Yongzhen Jiang | No issues

## TestCase-03
Testing Case for Survey Process (Desktop)
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-03 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
13/08/2025 | 1 | Visit the URL deployed to PythonAnywhere | The URL can be visited without any issue | The URL link works without any issue | PASS | Yongzhen Jiang | No issues
13/08/2025 | 2 | Click the Start Survey button | After the button is clicked, the survey page loads successfully | Survey starts correclty | PASS | Yongzhen Jiang | No issues
13/08/2025 | 3 | Click the pre-questions | The 2 pre-quenstions displays successfully | The pre-questions can be chosen and submitted | PASS | Yongzhen Jiang | No issues
13/08/2025 | 4 | Click the images that is preferred | 1. Images are loaded without any big delay 2. Images displays correctly | Images display correctly with a suitable size | PASS | Yongzhen Jiang | No issues
13/08/2025 | 5 | Choose the reasoning option in the final question and submit | The final question is clickable and can be submitted succeffully | Survey submitted successfully and the summary page displayed after submission | PASS | Yongzhen Jiang | No issues

## TestCase-04
Testing Case for Survey Process (Mobile)
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
iPhone 14 |  | Yongzhen Jiang | TC-04 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
14/08/2025 | 1 | Visit the URL deployed to PythonAnywhere via iPhone | The URL can be visited without any issue | The URL link works without any issue | PASS | Yongzhen Jiang
14/08/2025 | 2 | Click the Start Survey button | After the button is clicked, the survey page loads successfully | Survey starts correclty | PASS | Yongzhen Jiang
14/08/2025 | 3 | Click the pre-questions | The 2 pre-quenstions displays successfully | The pre-questions can be chosen and submitted | PASS | Yongzhen Jiang
14/08/2025 | 4 | Click the images that is preferred | 1. Images are loaded without any big delay 2. Images displays correctly | Images display correctly with a suitable size | PASS | Yongzhen Jiang
14/08/2025 | 5 | Choose the reasoning option in the final question and submit | The final question is clickable and can be submitted succeffully | Survey submitted successfully and the summary page displayed after submission | PASS | Yongzhen Jiang

## TestCase-05
Testing Case for survey UI styles
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-05 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
18/08/2025 | 1 | Click the Start Survey button | Should be able to login in successfully | Logged in successfully | PASS | Yongzhen Jiang | No issues
18/08/2025 | 2 | Check the pre-survey question options | The question shows correctly in a card | Question displays with a clear view | PASS | Yongzhen Jiang | No issues
18/08/2025 | 3 | Check the survey image pair page | 1. The progress bar on top displays correclty on each selection 2. Reminding text displays on top of the page 3. The two images are displayed in square shape and larger than 600px width | Images display with a large size, easy to recognize | PASS | Yongzhen Jiang | No issues
18/08/2025 | 4 | Final survey question | The final question shows in a card clearly | The final question displays correctly | PASS | Yongzhen Jiang | No issues
18/08/2025 | 5 | Survey completion summary page | Survey summary information is clearly shown in a card, with colorful number for invasive/non-invasive percentage | Summary information was clearly styled and displayed | PASS | Yongzhen Jiang | No issues

## TestCase-06
Testing Case for plant name display after survey completion
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-06 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
18/08/2025 | 1 | Start and conduct a survey | Survey can be conducted successfully | Survey done successfully | PASS | Yongzhen Jiang | No issues
18/08/2025 | 2 | Click the Your Choice Detail button on the final page | The button is clickable | The button worked and page redirected to summary page | PASS | Yongzhen Jiang | No issues
18/08/2025 | 3 | Check the plant name | A list of plant names that were involved in the survey should be displayed, with different color for invasive/non-invasive plant | The list of plant names were displayed correctly with different color | PASS | Yongzhen Jiang | No issues

## TestCase-07
Testing Case for ranking of Bradley-Terry model scores
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-07 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
20/08/2025 | 1 | Login as admin user | Login successfully | Logged in without any issue | PASS | Yongzhen Jiang | No issues
20/08/2025 | 2 | Click the Bradley-Terry model tab in dashboard page | The page shows without any issue | The page lods with no problem | PASS | Yongzhen Jiang | No issues
20/08/2025 | 3 | Navigate to chart of Bradley-Terry score ranking | 1. The charts display correctly, the bars are sorted by the value of score 2. Other charts shoud display correctly as well | The visual bars in the charts are sorted correclty by the score values and other charts show without any issue | PASS | Yongzhen Jiang | No issues

## TestCase-08
Testing Case for Bradley-Terry mode calculation based on database source rather than static mock data
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-08 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
23/08/2025 | 1 | Login as admin user | Login successfully | Logged in without any issue | PASS | Yongzhen Jiang | No issues
23/08/2025 | 2 | Logout and conduct a new survey | The survey should be done successfully | Survey was done | PASS | Yongzhen Jiang | No issues
23/08/2025 | 3 | Login as admin user once again and check whether the charts changes | The charts in Bradley-Terry model page should be different than previous | The visual charts changed accordingly, which verified that the data source was from database, rather than from the static mock data | PASS | Yongzhen Jiang | No issues

## TestCase-09
Testing Case for response time recording
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-09 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
08/09/2025 | 1 | Conduct a new survey | Survey should be done successfully | Survey was done with no issue | PASS | Yongzhen Jiang | No issues
08/09/2025 | 2 | Login the MySQL workbench | The response time for each choice should be saved in the survey_results table | The response time was saved successfully in the response_time field in the survey_results table | PASS | Yongzhen Jiang | No issues

## TestCase-10
Testing Case for weighted Bradley-Terry model
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-10 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
11/09/2025 | 1 | Login as admin user | Should login successfully | Logged in | PASS | Yongzhen Jiang
11/09/2025 | 2 | Click the dashboard page | The dashboard page should display 6 rows of charts successfully | Totally 6 rows of charts are displayed | PASS | Yongzhen Jiang
11/09/2025 | 3 | Compare the unweighted and weighted charts | On each row, the left side is the unweighted chart, and the right side is the weighted chart. There should be slightly difference between the two charts for each type. | 1. On each row, two charts were successfully displayed. Left is the unweighted version, and the right is the weighted version. 2. There were slighted differece between the two versions | PASS | Yongzhen Jiang

## TestCase-11
Testing Case for raw data display and downloading
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-11 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
13/09/2025 | 1 | Login as admin user | Should login successfully | Logged in | PASS | Yongzhen Jiang
13/09/2025 | 2 | Click the dashboard page | The dashboard page should display 6 rows of charts successfully | Totally 6 rows of charts are displayed | PASS | Yongzhen Jiang
13/09/2025 | 3 | Check the datatable in overall page and download function | 1. the datatable is listed with pagination 2. click the download button, the data should be downloaded in a csv file | 1. On each row, two charts were successfully displayed. Left is the unweighted version, and the right is the weighted version. 2. There were slighted differece between the two versions | PASS | Yongzhen Jiang
13/09/2025 | 4 | Check the datatable in by age group page and download function | 1. the datatable is listed with pagination 2. click the download button, the data should be downloaded in a csv file | 1. datatable was successfully displayed and downloaded 2. the data matched to the raw data in the database | PASS | Yongzhen Jiang
13/09/2025 | 5 | Check the datatable in by gardenning page and download function | 1. the datatable is listed with pagination 2. click the download button, the data should be downloaded in a csv file | 1. datatable was successfully displayed and downloaded 2. the data matched to the raw data in the database | PASS | Yongzhen Jiang
13/09/2025 | 6 | Check the datatable in by Bradley-Terry page and download function | 1. datatable should be displayed under each section of charts, which correspond to the chart data 2. Click the download button, the data should be downloaded successfully in a csv file | 1. datatable was successfully displayed and downloaded 2. the data matched to the raw data in the database | PASS | Yongzhen Jiang

## TestCase-12
Testing Case for survey cycle function
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-12 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
13/09/2025 | 1 | Login as admin user | Should login successfully | Logged in | PASS | Yongzhen Jiang
13/09/2025 | 2 | Click the survey cycle menu under site administration | the survey cycle page should be successfully loaded | The survey cycle page displayed successfully with a datatable for survey cycles | PASS | Yongzhen Jiang
13/09/2025 | 3 | Click the close button on the current survey | 1. The current survey cycle should be closed and a new cycle is started 2. If there's no survey available inside current cycle, application should give some warning | 1. Current survey cycle was closed, a new row as current cycle in the table was created automatically 2. System reminded me to fill some survey results if I click the close button for a new cycle | PASS | Yongzhen Jiang

## TestCase-13
Testing Case for end user testing
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-13 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
16/09/2025 | 1 | End user testing for a survey | The survey is conducted and completed successfully on mobile phone | Survey was done without any issue and the data was saved into the database | PASS | Huiwen Zhang (graduate student)
16/09/2025 | 2 | End user testing for a survey | The survey is conducted and completed successfully on mobile phone | Survey was done without any issue and the data was saved into the database | PASS | Rongbin Liu (graduate student)
16/09/2025 | 3 | End user testing for a survey | The survey is conducted and completed successfully on mobile phone | Survey was done without any issue and the data was saved into the database | PASS | Cai Lin (graduate student)
17/09/2025 | 4 | End user testing for a survey | The survey is conducted and completed successfully on mobile phone | Survey was done without any issue and the data was saved into the database | PASS | Bush (under-graduate student)

## TestCase-14
Testing Case for survey cycle data downloading function
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-15 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
20/09/2025 | 1 | Login as admin user | should be able to login successfully | logged in without any issue | PASS
20/09/2025 | 2 | Click the survey cycle page under site administration menu | the survey cycle page should displays correctly and each row in the table has a download icon | the download icon displayed correctly in the action column of the data table | PASS
20/09/2025 | 3 | Click the download icon for each survey cycle | a zip file is generated which includes both raw survey data and analysis data specific for that survey cycle | the icon was clickable and a zip file was automatically downloaded with csv files inside it | PASS

## TestCase-15
Testing Case for inversed response time as weighting
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-16 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
20/09/2025 | 1 | Check the log likelihood funtion in Python | the weight should be calculated as the inverse of response time, with a plus of very small value (10e-9) to avoid zero division | the code was updated correctly | PASS
20/09/2025 | 2 | Add debug information, to print out the original response time and weight | Print both the original response time and the weight calculated | the information was printed out successfully | PASS
20/09/2025 | 3 | Verify the output debug information | the weighting should be the inverse of the original response time | the weighting was calculated as inverse of the response time | PASS

## TestCase-16
Testing Case for quick naviation button in dashboard page
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-17 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
20/09/2025 | 1 | Login as admin user | should login successfully | Logged in successfully | PASS
20/09/2025 | 2 | Click the Bradley-Terry model tab in the dashboard page | the dashboard should display correctly and the quick navigation button is displayed | the navigation button displayed correclty | PASS
20/09/2025 | 3 | Click the hovered quick navigation button | 1. A list of links should be displayed in a off-canvas after click 2. Click each link will navigate the page to each section of the chart | the links worked without any issue | PASS

## TestCase-17
Testing Case for API function calling OpenAI nano model
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-18 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
23/09/2025 | 1 | Create a public api controller to call OpenAI nano model with get method for testing only | the API Key was successfully set, and API Url should be accessible | the urls was accessible from HttpPie client | PASS
23/09/2025 | 2 | Call the api from HttpPie | After a few seconds, the api should return a long text, which contains 2-3 paragraphs introduction about the plant, with invasiveness | the text successfully returned from the api controller | PASS

## TestCase-18
Testing Case for AI generated plant introduction
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-19 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
23/09/2025 | 1 | Conduct a new survey | the survey should be done successfully | the survey was done without any issue | PASS
23/09/2025 | 2 | Click the Your Choices button on completion of the survey | A list of plant names should be shown, with different color for invasive/non-invasive plants | a list of plant names with red or green color were displayed | PASS
23/09/2025 | 3 | Click each plant name displayed | 1. An off-canvas should be displayed on the right side 2. Text (2-3 paragraphs) should be displayed after clicking on each plant name. These text are generated by OpenAI | the AI powered description were displayed successfully | PASS

## TestCase-19
Testing Case for typing effect of the AI generated description of the plant
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-20 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
24/09/2025 | 1 | Conduct a new survey | the survey should be done successfully | the survey was done without any issue | PASS
24/09/2025 | 2 | Click the Your Choices button on completion of the survey | A list of plant names should be shown, with different color for invasive/non-invasive plants | a list of plant names with red or green color were displayed | PASS
24/09/2025 | 3 | Click each plant name displayed | The text should be automatically displayed on the off-canvas component with an effect of typing. Characters are displayed one by one with a small time slap. | the display effect worked as expected | PASS

## TestCase-20
Testing Case for plant list and plant adding and editing
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-21 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
26/09/2025 | 1 | Loggin as admin user | should login successfully | logged in without any issue | PASS
26/09/2025 | 2 | Click the Plant List sub-menu under site administration menu | the plant list page should displayed correctly with colorful action buttons | the plant list page showed with a new looking | PASS
26/09/2025 | 3 | Click the Add Plant button | should redirect to the addd plant page | the add plant page worked well and new plant was successfully created | PASS
26/09/2025 | 4 | Click the Edit button | should redirect to the edit plant page | the edit page and function worked without issue | PASS
26/09/2025 | 5 | Click the delete button | should confirmation deletion of the plant and if yes, the plant should be deleted | the deletion function worked as expected | PASS
26/09/2025 | 6 | Click the Add Plant sub-menu under site administration menu | should redirect to the addd plant page | the Add Plant page worked with no issue | PASS

## TestCase-21
Testing Case for profile edit
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-22 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
30/09/2025 | 1 | Loggin as admin user | should login successfully | logged in without any issue | PASS
30/09/2025 | 2 | Click the my profile sub-menu under the user icon menu | the my profile page should be displayed, with profile icon image, and a map displaying the location | the my profile page was shown without any issue | PASS
30/09/2025 | 3 | Click the Update Profile button | profile edit page should be shown | edit page displayed | PASS
30/09/2025 | 4 | Update the profile with a new profile image | the profile image should be able to replaced with a new image | the image was successfully replaced | PASS
30/09/2025 | 5 | Input some text in the location input field | a list of recommeded locations should be displayed which are fetched from OpenStreetMap via api | a few recommended location names related to what I input was listed as a drop down list | PASS
30/09/2025 | 6 | Click the Update Profile button | the profile information like email, name or location should be able to be updated | profile information updated successfully | PASS

## TestCase-22
Testing Case for survey cycle master detail tables
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-23 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
03/10/2025 | 1 | Loggin as admin user | should login successfully | logged in without any issue | PASS
03/10/2025 | 2 | Go to the survey cycle page | the survey cycle master table should be displayed without any issue | the page loaded correctly | PASS
03/10/2025 | 3 | Click any row in the survey cycle table | a detailed table should be shown under the master survey table | the detailed table was displayed as expected | PASS
03/10/2025 | 4 | Click the delete icon in the detail table | A single survey record should be deleted successfully, and the detailed table should be refreshed | the data was deleted and the table was refreshed correctly | PASS
03/10/2025 | 5 | Click the Update button within the action column in the master table | the analysis model within that cycle should be recalculated and updated | 1. the raw survey data and analysis data within that cycle was refreshed and updated correctly 2. The downloaded data was updated as well | PASS

## TestCase-23
Testing Case for survey cycle summary table
PROJECT NAME |  |  |  |  | SPECIAL NOTES
Plant Choice (GreenMean) Project
BROWSER |  | WRITTEN BY | TEST CASE ID | VERSION
Microsoft Edge Version 141.0.3537.71 |  | Yongzhen Jiang | TC-24 | 1.0
DATE | TEST No. | DESCRIPTION | EXPECTED RESULT | ACTUAL RESULT | PASS / FAIL | TESTED BY | TESTER COMMENTS
05/10/2025 | 1 | Loggin as admin user | should login successfully | logged in without any issue | PASS
05/10/2025 | 2 | Go to the survey cycle page | at the top a table should be shown which displays the summary data for all survey results | the summary table displayed the summary including number of participants and total survey choices | PASS
05/10/2025 | 3 | delete some records in one survey cycle, and then click the Update button in the survey summary table | the raw survey data and analysis data for all survey results should be updated after deletion | 1. the data was updated successfully 2. the downloaded data was updated as well | PASS